## Cover Page
Project Name | Plative
Version: | 1.0.0

## Test execute report
Test case execute Report
Group | Feature | Sub feature | Total TCs |  | Executed TCs | [5 empty] | Not execute TCs | [5 empty] | Blocked TCs |  | Comment
|  |  | Group ID | Total | Summary |  | Group by status |  |  |  | Summary |  | Group by status |  |  |  | Total | Rate (%)
[5 empty] | Executed TCs |  | Passed |  | Failed |  | Not execute TCs |  | Not Run |  | N/A
[5 empty] | Total | Rate (%) | Total | Rate (%) | Total | Rate (%) | Total | Rate (%) | Total | Rate (%) | Total | Rate (%)
Group chat |  |  |  | 146 | 121 | 82.88% |  |  |  |  | 22 | 15.07% | 0 | 0% | 2 | 1.37%
| Check login |  |  | 3 | T | 3 | Pass |  | Fail |  | NT |  | Not Run |  | N/A |  | Blocked
|  | Not login | Chat - Login - Not | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Logged in | Chat - Login - Yes | 2 | 2 | 100% | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
| Message chat |  |  | 134
|  | Header | Chat - Msg - Header | 10 | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 100% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Footer | Chat - Msg - Footer | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 100% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Category | Chat - Msg - Category | 6 | 6 | 100% | 5 | 83.33% | 1 | 16.67% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Target | Chat - Msg - Target | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Chat title | Chat - Msg - Title | 7 | 7 | 100% | 6 | 85.71% | 1 | 14.29% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Chat conversation | Chat - Msg - Conversation | 49 | 48 | 97.96% | 41 | 83.67% | 7 | 14.29% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Upload file | Chat - Msg - Upload file | 39 | 39 | 100% | 34 | 87.18% | 5 | 12.82% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Download file | Chat - Msg - Download | 4 | 3 | 75% | 3 | 75% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 25% | 0 | 0%
|  | Delete file | Chat - Msg - Del File | 3 | 3 | 100% | 2 | 66.67% | 1 | 33.33% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Chat footer | Chat - Msg - Footer | 6 | 0 | 0% | 0 | 0% | 0 | 0% | 6 | 100% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Error | Chat - Msg - Error | 3 | 3 | 100% | 3 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
| Category logic |  |  | 3
|  | List item | Chat - Category - List | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Select item | Chat - Category - Select | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Change another item | Chat - Category - Change | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
| Target logic |  |  | 6
|  | Show list item follow selected category | Chat - Target - List | 5 | 4 | 80% | 4 | 80% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 20% | 0 | 0%
|  | Change another item | Chat - Category - Change | 1 | 1 | 100% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%

## Test case
TEST CASE
Group Feature | Feature | TCs ID | TC Name | Type | Priority | Test case detail |  |  | Test action (T, N) | Test status | Test Date (mm-dd-yyyy) | Tested By | Count bugs
[6 empty] | Input data | Steps | Expected Result
Group chat
Check login
Not login
| Chat - Login - Not | 002 | User use direct link access page | FUN | Normal |  | 1. Login to page 2. Go to chat 3. Copy link at url 4. Log out 5. Paste link on browser | Go to login page | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
Logged in
| Chat - Login - Yes | 004 | User login: use direct link access page | FUN | High |  | 1. Login with parent account 2. Go to chat 3. Copy link 4. Go to another page 5. Paste link on browser | Go to chat page | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
| Chat - Login - Yes | 005 | User login: use direct link access page | FUN | High |  | 1. Login with sub account 2. Go to chat 3. Copy link 4. Go to another page 5. Paste link on browser | Go to chat page | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
Log out
| Chat - Log out | 007 | User log out at chat page | FUN | Normal |  | 1. Login with parent account 2. Go to chat 3. Log out | Go to login page | NT |  |  |  | 0
| Chat - Log out | 008 | User log out at chat page | FUN | Normal |  | 1. Login with sub account 2. Go to chat 3. Log out | Go to login page | NT |  |  |  | 0
Message chat
Header
| Chat - Msg - Header | 011 | Show BIZTECT Logo | FUN | Normal |  |  | Show correct logo | NT |  |  |  | 0
| Chat - Msg - Header | 012 | Check effect hover on logo | FUN | Low |  | Hover on logo | Display hand-shaped cursor | NT |  |  |  | 0
| Chat - Msg - Header | 013 | Check hover out logo | FUN | Low |  | Hover out logo | Display "I" cursor | NT |  |  |  | 0
| Chat - Msg - Header | 014 | Click to logo | FUN | Low |  | Logged in with parent account | Go to page BIZTECT TOP [Screen ID: B000000]. | NT |  |  |  | 0
| Chat - Msg - Header | 015 | Can not click | FUN | Low |  | Logged in with sub account | Disable click action | NT |  |  |  | 0
| Chat - Msg - Header | 016 | Show list action of parent account | FUN | Low |  | Show list item | 「マイページ」 「カート」 「お気に入り」 「ログアウト」 | NT |  |  |  | 0
| Chat - Msg - Header | 017 | Show list action of sub-account | FUN | Low |  | Show list item | 「ログアウト」 | NT |  |  |  | 0
| Chat - Msg - Header | 018 | Hide list action of sub-account | FUN | Low |  | Hide list item | 「マイページ」 「カート」 「お気に入り」 | NT |  |  |  | 0
| Chat - Msg - Header | 019 | Check effect hover on | FUN | Low |  | Hover on item | Display hand-shaped cursor | NT |  |  |  | 0
| Chat - Msg - Header | 020 | Check hover out logo | FUN | Low |  | Hover item | Display "I" cursor | NT |  |  |  | 0
Footer
| Chat - Msg - Footer | 022 | Show BIZTECT Logo | FUN | Low |  |  | Show correct logo | NT |  |  |  | 0
| Chat - Msg - Footer | 023 | Check effect hover on logo | FUN | Low |  |  | Display hand-shaped cursor | NT |  |  |  | 0
| Chat - Msg - Footer | 024 | Check hover out logo | FUN | Low |  |  | Display "I" cursor | NT |  |  |  | 0
| Chat - Msg - Footer | 025 | Show list footer item | FUN | Low |  |  | Show list item | NT |  |  |  | 0
| Chat - Msg - Footer | 026 | Check effect hover on | FUN | Low |  | Hover on item | Display hand-shaped cursor | NT |  |  |  | 0
| Chat - Msg - Footer | 027 | Check hover out logo | FUN | Low |  | Hover item | Display "I" cursor | NT |  |  |  | 0
Category
| Chat - Msg - Category | 029 | Default value | FUN | Normal |  |  | Show text（区分選択） | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
| Chat - Msg - Category | 030 | Check effect hover on | FUN | Low |  |  | Display hand-shaped cursor | T | Fail | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Category | 031 | Check effect hover out | FUN | Low |  |  | Display arrow cursor | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Category |  | Can not start chat |  |  |  | 1. Main account resisterd (no any sub account) 2. Site name not create for main account | 1. Can choose option "現場" 2. Can not choose target 3. Can not start chat | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
| Chat - Msg - Category |  | Can not start chat |  |  |  | 1. Main account resisterd (no any sub account) 2. Site name relationship with main account | 1. Can choose option "現場" 2. Can not choose target 3. Can not start chat | T | Pass | 2022-08-12 | Khánh Nguyễn | 0
| Chat - Msg - Category |  | Can start chat |  |  |  | 1. Main account resisterd 2. Register sub account 2. Site name relationship with main account | 1. Can choose option "現場" 2. Site name: show list site map 3. Can start chat | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
Target
| Chat - Msg - Target | 036 | Default value | FUN | Low |  |  | Show text (対象名称） | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
Chat title
| Chat - Msg - Title | 038 | Show chat title default if not choose category | FUN |  |  | 1. Start chat | Show text (対象名称） | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Title | 039 | Show chat title default if chosen category is 現場 but not choose target | FUN |  |  | 1. Start chat 2. Choose category is 現場 | Show text (対象名称） | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Title | 040 | Show chat tittle when chosen 現場 category and choose a 現場名 | FUN |  |  | 1. Start chat 2. Choose category is 現場 3. Choose a 現場名 | Show correct data 現場名 selected | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Title | 041 | Show chat tittle when chosen 現場 category and change to other 現場名 | FUN |  |  | 1. Start chat 2. Choose category is 現場 3. Choose a 現場名 4. Change to other 現場名 | Show correct data 現場名 selected | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Title | 042 | Show chat title default if chosen category is 会員 but not choose target | FUN |  |  | 1. Start chat 2. Choose category is 会員 | Show text (対象選択） | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Title | 043 | Show chat title if chosen category is 会員 and target is 全員 | FUN |  |  | 1. Start chat 2. Choose category is 会員 3. Choose taget is 全員 | Show title is 全員 | T | Fail | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Title | 044 | Show chat title if chosen category is 会員 and target is sub account name | FUN |  |  | 1. Start chat 2. Choose category is 会員 3. Choose taget is sub account name | Show title is sub account name | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
Chat conversation
| Chat - Msg - Conversation | 046 | Check color background | FUN | Normal |  |  | Gray color | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 047 | Show correct position of chat person | FUN | Normal |  |  | Show right side of the frame | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 048 | Show correct position of reply person | FUN | Normal |  |  | Show left side of the frame | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 049 | Show icon of reply persion: height & width | FUN | Normal |  |  | Height: 60px Width: 50px | T | Pass | 2022-08-15 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 050 | Show icon of reply persion: color | FUN | Normal |  |  | Color is white | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 051 | Check name of reply person: name | FUN | Normal |  |  | Show register name (name 01 + space + name02) | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 052 | Check name of reply person: font size | FUN | Normal |  |  | 10px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 053 | Check name of reply person: color | FUN | Normal |  |  | White | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 054 | Check space between left of box & chat frame | FUN | Normal |  |  | 70 px | T | Fail | 2022-08-15 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 055 | Check frame of chat: chat in a line | FUN | Normal |  |  | Follow requirement | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 056 | Check frame of chat: chat break to multi line | FUN | Low |  |  | Show chat multi line | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 057 | Check min of chat frame: a character | FUN | Low |  |  | Not requirement | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 058 | Check max of chat frame: max of a line | FUN | Normal |  |  | 5 px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 059 | Check space with other chat frame | FUN | Normal |  |  | 10 px | T | Fail | 2022-08-15 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 060 | Check space of chat content compare with chat frame | FUN | Normal |  |  | Left: 5 px Right: 5 px Top: 5 px Bottom: 5px | T | Fail | 2022-08-15 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 061 | Check radius of chat frame | FUN | Normal |  |  | Has radius | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 062 | Chat background color of chat frame (reply person side) | FUN | Normal |  |  | White | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 063 | Chat background color of chat frame (my side) | FUN | Normal |  |  | Lime | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 064 | Check color of chat content | FUN | Normal |  |  | Font color: black Font sixe: 12 px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 065 | Check padding between right & chat content | FUN | Normal |  |  | 5 px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 066 | Check time: format of date time | FUN | Normal |  |  | Line 1: YYYY/MM/DD (date of chat) Line 2: hh:mm (24 hours) | T | Fail | 2022-08-15 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 067 | Check time: position will show - right side | FUN | Normal |  |  | Show right side of the frame | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 068 | Check time: position will show - right side | FUN | Normal |  |  | Top & right side of chat frame | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 069 | Check time: format of text | FUN | Normal |  |  | Font color: white Font sixe: 9 px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 070 | Check scroll: if chat conversation too long | FUN | Normal |  |  | Show scroll | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 071 | Check scroll: scroll auto scale small when chat too many | FUN | Low |  |  | Auto scale height of scroll | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 072 | Auto scroll to bottom of chat conversation | FUN | Low |  | 1. Current stay top of chat conversation 2. Has new message | Auto scroll bottom of chat conversation | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 073 | Check focus | FUN | Low |  |  | Auto focus at newest chat | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 074 | Chat history: history < 30 chat time | FUN | Normal |  |  | Show all chat: correct number of chat time & chat content | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 075 | Chat history: history = 30 chat time | FUN | Low |  |  | Show all chat: correct number of chat time & chat content | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 076 | Chat history: history > 30 chat time | FUN | Normal |  |  | Only show 30 line chat newest | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 077 | Check time show new message | FUN | Low |  |  | Less than 1s | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 078 | Check hot key | FUN | Low |  |  | Can not use hot key [Shift] + [Enter] for enter | T | Fail | 2022-08-17 | Khánh Nguyễn | 1
Upload file
| Chat - Msg - Upload file | 080 | Show icon upload file | FUN | Normal |  |  | Show at left side and below chat box | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 081 | Check width, height of icon | FUN | Normal |  |  | Hight: 30 px Width: 30 px Color: white | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 082 | Space of upload file with other | FUN | Normal |  |  | Left: 5 px Right 10 px Top: 5px Bottom: 5 px | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 083 | Effect when hover on | FUN | Normal |  |  | Display hand-shaped cursor | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 084 | Click & select file upload | FUN | Normal |  |  | Can click icon Can select file | T | Pass | 2022-08-15 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 085 | Click but not upload file | FUN | Normal |  |  | Back to chat conversation | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 086 | Show date & time of file upload | FUN | Normal |  |  | Line 1: YYYY/MM/DD (date of chat) Line 2: hh:mm (24 hours) | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 087 | Show date & time of file upload: format | FUN | Normal |  |  | Color: white Size: 9 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 088 | Show icon of uploaded file: space | FUN | Normal |  |  | Left: 5 px Right 5 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 089 | Show icon of uploaded file: format | FUN | Normal |  |  | Color: white Height: 36 px Width: 36 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 090 | Show icon of deleted file: format | FUN | Normal |  |  | Color: #CCCCCC Hight: 60 px Width: 50 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 091 | Show name of file | FUN | Normal |  |  | Name + file type | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 092 | Show name of file: space | FUN | Normal |  |  | Right: 5px Max width: 100px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 093 | Show name of file: multi line | FUN | Normal |  |  | Auto enter the new line if with greater than 100 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 094 | Show name of file: format | FUN | Normal |  |  | Color: white Size: 10 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 095 | View my upload file: Show delete icon | FUN | Normal |  |  | Right side of file | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 096 | View my upload file: click icon | FUN | Normal |  |  | Image file: can view | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 097 | View my upload file: click icon | FUN | Normal |  |  | Other file type: can not view | T | Fail | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Upload file | 098 | Popup menu | FUN | Normal |  |  | Hight: 80 px Width: 120 px Color: white Font size: 12 px Font color: white Shadow: drop shadow File type: png, jpeg, jpg | T | Fail | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Upload file | 099 | Close popup | FUN | Normal |  |  | Click out of popup & close popup | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 100 | Check upload multi file | FUN | Normal |  |  | Can not do it | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 101 | Auto create folder upload file | FUN | Normal |  | 1. Start upload file 1st | Auto create folder save file | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 102 | Check limit all file | FUN | Normal |  |  | Total all file < 5GB can upload | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 103 | Upload file medium size | FUN | Normal | Use file 512 MB |  | Can upload | T | Fail | 2022-08-17 | Khánh Nguyễn
| Chat - Msg - Upload file | 104 | Upload file too large | FUN | Normal | Use file 1 GB |  | Can upload | T | Fail | 2022-08-17 | Khánh Nguyễn | 1
| Chat - Msg - Upload file | 105 | Can upload file type | FUN | Normal | pdf |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 1
| Chat - Msg - Upload file | 106 | Can upload file type | FUN | Normal | csv |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 107 | Can upload file type | FUN | Normal | xlsx |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 108 | Can upload file type | FUN | Normal | doc |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 109 | Can upload file type | FUN | Normal | docx |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 110 | Can upload file type | FUN | Normal | pptx |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 111 | Can upload file type | FUN | Normal | png |  | Can upload & preview | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 112 | Can upload file type | FUN | Normal | jpeg |  | Can upload & preview | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 113 | Can upload file type | FUN | Normal | jpg |  | Can upload & preview | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 114 | Can upload file type | FUN | Normal | txt |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 115 | Can upload file type | FUN | Normal | mp4 |  | Can upload | T | Fail | 2022-08-17 | Khánh Nguyễn | 1
| Chat - Msg - Upload file | 116 | Can upload file type | FUN | Normal | rar |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 117 | Can upload file type | FUN | Normal | zip |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Upload file | 118 | Can upload file type | FUN | Normal | mp3 |  | Can upload | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
Chat conversation
| Chat - Msg - Conversation | 120 | Show text of place holder | FUN | Normal |  |  | Show test "メッセージを入力" | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 121 | Check space with bottom icon | FUN | Normal |  |  | Bottom: 5 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 122 | Can enter chat content to message box | FUN | Normal |  |  | Can enter content | T | Pass | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Conversation | 123 | Expand height of chat box | FUN | Low |  |  | Can not do it | T | Fail | 2022-08-17 | Khánh Nguyễn
| Chat - Msg - Conversation | 124 | Check background color | FUN | Normal |  |  | Color is black | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 125 | Check format of box | FUN | Normal |  |  | Height: 48 px Width: 60% | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 126 | Check format text of box | FUN | Normal |  |  | Color: white Font size: 14 px | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 127 | Check text of button send message | FUN | Normal |  |  | Show text "送信" Font size: 14 px Font color: white | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 128 | Check chat Construction Site - main acc with 1 sub account | FUN | High |  | 1. Create 1 construction site 2. Create 1 sub account for main account 3. Go to construction site chat conversation 4. Start chat & check result | Can chat & show correct data | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 129 | Check chat Construction Site - main acc with 2 sub account | FUN | High |  | 1. Create 1 construction site 2. Create 1 sub account for main account 3. Go to construction site chat conversation 4. Start chat 5. Create 1 new sub account 6. New sub account go to above chat conversation | 1. New account can view chat history 2. New acc can start chat | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 130 | Check chat Construction Site - main acc with 3 sub account | FUN | High |  | 1. Create 1 construction site 2. Create 1 sub account for main account 3. Go to construction site chat conversation 4. Start chat 5. Create 1 new sub account 6. New sub account go to above chat conversation 7. Repeat step 5&6 | 1. New account can view chat history 2. New acc can start chat | T | Pass | 2022-08-17 | Khánh Nguyễn | 0
| Chat - Msg - Conversation | 131 | Check chat Construction Site - sub account of other main account | FUN | High |  |  | Can not show site. Can not start chat | T | Pass | 2022-08-17 | Khánh Nguyễn
| Chat - Msg - Conversation | 132 | Check chat member - main acc with 1 sub account | FUN | High |  |  | Can chat & show correct data | T | Pass | 2022-08-17 | Khánh Nguyễn
| Chat - Msg - Conversation | 133 | Check chat member - main acc with all sub account | FUN | High |  |  | Can chat & show correct data | T | Fail | 2022-08-17 | Khánh Nguyễn
| Chat - Msg - Conversation | 134 | Check chat member - sub acc with other sub account | FUN | High |  |  | Can chat & show correct data
| Chat - Msg - Conversation | 135 | Check chat member - main acc with 1 sub account of other main account | FUN | High |  |  | Main acc side: - Not show member - Can not start chat Sub acc side: - Not show main acc - Can not start chat | T | Pass | 2022-08-17 | Khánh Nguyễn
Error
| Chat - Msg - Error | 137 | Check layout of error message box | FUN | Low |  |  | Height: 30% Width: 60% Background color: #666666 Font size: 24px Text format: bold Text color: white | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Error | 138 | Check close popup | FUN | Low |  | Click button "X" | Close popup | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Error | 139 | Check close popup | FUN | Low |  | Click out of popup | Close popup | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
Delete file
| Chat - Msg - Del File | 141 | Show popup confirm | FUN | High |  | Click button delete |  | T | Pass | 2022-08-16 | Khánh Nguyễn | 1
| Chat - Msg - Del File | 142 | Can delete file | FUN | High |  | 1. Click button delete 2. Click button confirm | Delete file success Show text 削除済み at file position | T | Fail | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Del File | 143 | Not delete file | FUN | Normal |  | 1. Click button delete 2. Click out side of popup | Not delete file | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
Download file
| Chat - Msg - Download | 145 | Can download file | FUN | Normal |  | Click file name | Download file | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Download | 146 | Can download file | FUN | Normal |  | Click file icon | Download file | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Msg - Download | 147 | Download file but network has problem | FUN | Low |  | 1. Click download file 2. Disconnect internet | Can not download file | N/A |  |  |  | 0
| Chat - Msg - Download | 148 | Download file but file just delete | FUN | Low |  | 1. Click download file deleted | Show error message "ファイルが存在しません。" | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
|  |  | Can download file - my side | FUN | Low | pdf |  | Can download | T | Pass
|  |  | Can download file - my side | FUN | Low | csv |  | Can download
|  |  | Can download file - my side | FUN | Low | xlsx |  | Can download
|  |  | Can download file - my side | FUN | Low | doc |  | Can download
|  |  | Can download file - my side | FUN | Low | docx |  | Can download | T | Pass
|  |  | Can download file - my side | FUN | Low | pptx |  | Can download
|  |  | Can download file - my side | FUN | Low | png |  | Can download
|  |  | Can download file - my side | FUN | Low | jpeg |  | Can download
|  |  | Can download file - my side | FUN | Low | jpg |  | Can download
|  |  | Can download file - my side | FUN | Low | txt |  | Can download
|  |  | Can download file - my side | FUN | Low | mp4 |  | Can download
|  |  | Can download file - my side | FUN | Low | rar |  | Can download
|  |  | Can download file - my side | FUN | Low | zip |  | Can download
|  |  | Can download file - my side | FUN | Low | mp3 |  | Can download
|  |  | Can download file - the other side | FUN | Normal | pdf |  | Can download
|  |  | Can download file - the other side | FUN | Normal | csv |  | Can download
|  |  | Can download file - the other side | FUN | Normal | xlsx |  | Can download
|  |  | Can download file - the other side | FUN | Normal | doc |  | Can download
|  |  | Can download file - the other side | FUN | Normal | docx |  | Can download
|  |  | Can download file - the other side | FUN | Normal | pptx |  | Can download
|  |  | Can download file - the other side | FUN | Normal | png |  | Can download
|  |  | Can download file - the other side | FUN | Normal | jpeg |  | Can download
|  |  | Can download file - the other side | FUN | Normal | jpg |  | Can download
|  |  | Can download file - the other side | FUN | Normal | txt |  | Can download
|  |  | Can download file - the other side | FUN | Normal | mp4 |  | Can download
|  |  | Can download file - the other side | FUN | Normal | rar |  | Can download
|  |  | Can download file - the other side | FUN | Normal | zip |  | Can download
|  |  | Can download file - the other side | FUN | Normal | mp3 |  | Can download
Category logic
| Chat - Category - List | 178 | Show list item | FUN | Low |  |  | Show 2 item: 現場, 会員 | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Category - Select | 179 | Can select item at list | FUN | Normal |  |  | Can select 1 item | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Category - Change |  | Can change to other item | FUN | Low |  |  | Can change to other option | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
Target logic
| Chat - Target - List | 182 | Select 現場 - Not register yet | FUN | Low |  |  | 1. Can not choose 2. Can not start chat | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Target - List | 183 | Select 現場 - Registered | FUN | Low |  |  | Can choose | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Target - List |  | Check format show construction site | FUN | Low |  |  | Site_name | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Target - List | 185 | Select 会員 - Empty sub account | FUN | Low |  |  | 1. Only show option "全員" 2. Can not select 3. Can not start chat | N/A |  |  |  | 0
| Chat - Target - List | 186 | Select 会員 - Has 1 sub account | FUN | Low |  |  | Show 2 option: "全員" Sub account name | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Target - Change | 187 | Select 会員 - Has more 1 sub account | FUN | Low |  |  | Show option "全員" & list sub account (sort by id) | N/A |  |  |  | 0
| Chat - Target - Change | 188 | Select 会員 - Can not select my account | FUN | Low |  |  | Not show my account at list account | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
| Chat - Target - Change | 189 | Check format show sub account | FUN | Low |  |  | Show name is: "name01 + Half-width space + name02" | T | Pass | 2022-08-16 | Khánh Nguyễn | 0
|  | 190 |  | FUN | [8 empty] | 0
|  | 191 |  | FUN | [8 empty] | 0

## Bug list
BUGS LIST
Feature | Bug ID | TCs ID | Bug name | Bug description | Bug image | Status | Priority | Note
Chat - Msg - Conversation | 1 | 049 | Chiều cao và chiều rộng của icon avatar chưa đúng với yêu cầu | Curent: Height: 36px Width: 36 px Expect: Heght: 60 px Width: 50px | https://drive.google.com/file/d/16wvHI-XCcqBIAwGQ_kLdPQnE8H0fmHmu/view?usp=sharing | Reject | Low | QA_Biztect_VN - Google Trang tính QA kh mục 11
Chat - Msg - Conversation | 2 | 054 | Khoảng cách từ lề trái của khung chat đến | Hiện tại: khoảng cách khoảng 110 px Mong muốn: 70 px | https://drive.google.com/file/d/1mp-bD7Hn9yCIuNTKJJ6HfXy-HzOmnC8t/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 3 |  | Button sent bị disable khi nội dung chat < 4 characters | Hiện tại: - Khi nhập nội dung <= 3 ký tự: button sent bị disable (enter thì vẫn gửi nội dung chat đi được) - Khi nhập >= 4 ký tự: button sent enable Mong muốn: - Khi đã nhập 1 ký tự thì button sent sẽ enable | https://drive.google.com/file/d/1D_aiAVu0l-VIOtXvMT12cP597TYP4HQo/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 4 | 059 | Khoảng cách giữa 2 dòng tin nhắn chưa đúng như docs mô tả | Hiện tại: - Phía người chat xem tin nhắn của người reply: khoảng cách giữa 2 bóng chat khoảng 30px - Phía người chat xem tin nhắn của mình: khoảng cách khoảng 16px Mong muốn: - 10px cho khoáng cách của 2 bóng chat | https://drive.google.com/file/d/18yfwIW4Dvf17AdF_U_8vP9j3o2hcCw12/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 5 | 060 | Khoảng cách giữa text và lê của bong bóng thoại chưa đúng | Hiện tại: - Padding: 6px 8px Mong muốn: - Padding: 5px | https://drive.google.com/file/d/1MHgfg7tMg8NyS8oWFLYrz6PHpj_0Wq35/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 6 | 066 | Format time chưa đúng | Hiện tại: - Đang hiển thị là: YYYY-MM-DD hh:mm Mong muốn: - YYYY/MM/DD hh:mm | https://drive.google.com/file/d/1bOIPqq05KNKpcqqKk_ZiPtLRLBqnTHLJ/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 7 |  | Bỏ sự kiện enter thì con trỏ xuống dòng trong khung nhập tin nhắn | Hiện tại: - Khi nhấn enter trong khung chat thì hiện tại con trỏ nhập tin nhắn được nhảy xuống hàng (dễ nhầm tưởng thành có thể xuống hàng nhưng thực tế là tin nhắn được gửi đi) Mong muốn: - Sau khi nhấn enter thì tin nhắn được gửi đi (như hiện tại) nhưng con trỏ không xuống hàng mới | https://drive.google.com/file/d/1O0K0xpnQadSZWyCWeQiwKnpHQ0pgM_Gk/view?usp=sharing | Fixed | Low | mục 2.3.1 kh note nhấn enter sẽ xuống hàng chỉ nhấn nút mới gửi tin nhắn
Chat - Msg - Category | 8 | 030 | Chưa có effect đổi con trỏ chuột thành bàn tay khi hover lên field chọn category và target | Hiện tại: - Khi hover lên field chọn category và target con trỏ chuột thành bàn tay Mong muốn: - Đổi con trỏ chuột thành bàn tay khi hover on lên field category và target | https://drive.google.com/file/d/1XqQT365ac4X1WuY6UTShQR8W8wNSdHmz/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 9 |  | Limit số lượng ký tự được phép chat | Tối đa: 4000 characters Từ 4001 sẽ không cho chat nữa | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Upload file | 10 |  | Upload file: bỏ phần limit 2 MB cho 1 file | Upload file: bỏ phần limit 2 MB cho 1 file | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Upload file | 11 |  | Tên file: hiển thị tên file mà user đã upload (không rename lại tên file) | Tên file: hiển thị tên file mà user đã upload (không rename lại tên file) | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Upload file | 12 |  | Preview file image: có thể xem được file image không phân biệt người upload |  | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Download | 13 |  | Download file: file mình tài lên thì mình cũng có thể download |  | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Target | 14 | 043 | Thêm option chat all khi chọn category là 会員 |  | Note từ file Q&A qua | Fixed | Normal
Chat - Msg - Upload file | 15 | 097 | Chưa ẩn option preview khi file type không phải là hình ảnh | Hiện tại: - Khi nhấn vào file đã upload không phải là file image (.png, .jpeg, .jpg) thì option preview vẫn được hiển thị Mong muốn: - Nếu file type không phải là image thì ẩn option preview | https://drive.google.com/file/d/1cpWKRPTjWsdomLxF-iGrOpFZDSJ1WoCE/view?usp=sharing | Fixed | Normal
Chat - Msg - Upload file | 16 | 098 | Thiếu shadow trên popup chọn preview hoặc download file | Hiện tại: - Menu để chọn option preview hoặc download chưa có shadow Mong muốn: - Bổ sung shadow | https://drive.google.com/file/d/1ythNa8r_O8CvvYxIzbRov7w31cC2898_/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 17 |  | Chưa có nội dung trong trường hợp offline và nhấn nút Sent sau khi đã nhập nội dung chat | Hiện tại: - Hiển thị text "undefine" Mong muốn: - Nhờ anh Tâm cho nội dung câu thông báo |  | New | Low
Chat - Msg - Upload file | 18 |  | Chưa có nội dung trong trường hợp offline và nhấn nút Sent sau khi đã upload file | Hiện tại: - Hiển thị text "undefine" Mong muốn: - Nhờ anh Tâm cho nội dung câu thông báo |  | New | Low
Chat - Msg - Upload file | 19 |  | Chưa có nội dung trong trường hợp offline trong quá trình upload file | Hiện tại: - Hiển thị text "undefine" Mong muốn: - Nhờ anh Tâm cho nội dung câu thông báo |  | New | Low
Chat - Msg - Del File | 20 | 141 | File đã xóa nhưng chưa hiển thị text đã xóa, sau khi repoad page thì mới hiển thị | Hiện tại: - File đã bị xóa chưa hiển thị text 削除済み - Sau khi reload page sẽ hiển thị text 削除済み Mong muốn: - Sau khi đã xóa xong file thì hiển thị text 削除済み | https://drive.google.com/file/d/1cGyBj9AG426NITGyRanAelco4yp6MFDl/view?usp=sharing | Fixed | Normal
Chat - Msg - Conversation | 21 | 122 | Xóa chức năng expand của text area của field nhập nội dung chat | Hiện tại: - Khung nhập nội dung chat có thể kéo to ra hoặc nhỏ lại (mặc định của text area) Mong muốn: - Bỏ phần có thể dùng chuột để kéo rộng hoặc thu nhỏ của field nhập nội dung chat | https://drive.google.com/file/d/1mc4aNEMIp-G69wHedLNc1mR3o9WHcr5G/view?usp=sharing | Fixed | Low
Chat - Msg - Upload file | 22 | 115 | Không thể upload file có đuôi mp4 | Hiện tại: - Báo lỗi 500 internal server error khi upload file có đuôi mp4 Mong muốn: - Có thể upload file | https://drive.google.com/file/d/1u-qWUT974rcvBpUayVKxBPVs-pevu1OG/view?usp=sharing | Fixed | Normal
Chat - Msg - Upload file | 23 | 104 | Không thể upload file có dung lượng lớn: 1 GB | Hiện tại: - Báo lỗi 500 internal server error khi upload file dung lượng lớn 1 GB Mong muốn: - Có thể upload file | https://drive.google.com/file/d/1UjDJs6QVDFCdQ2Payv3wQR8c_dCCHq_k/view?usp=sharing | Fixed | Low
Chat - Msg - Upload file | 24 | 105 | Không thể upload file có dung lượng hơi lớn: 512 MB | Hiện tại: - Báo lỗi 500 internal server error khi upload file dung lượng tương đối lớn khoảng 600 MB Mong muốn: - Có thể upload file | https://drive.google.com/file/d/1UjDJs6QVDFCdQ2Payv3wQR8c_dCCHq_k/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 25 | 078 | Có thể dùng tổ hợp phím Shift + Enter để xuống hàng trong text area nhập nội dung chat | Hiện tại: - Có thể dùng tổ hợp phím Shift + Enter để xuống hàng Mong muốn: - Không cho xuống hàng khi dùng tổ hợp phím Shift + Enter | https://drive.google.com/file/d/1O3M3EGhgufjO7kPeEcPndRkgMeNOu1ns/view?usp=sharing | Fixed | Low
Chat - Msg - Conversation | 26 | 133 | Tin nhắn không hiển thị đồng bộ ở các acc khác nhau | Hiện tại: - Mở cùng lúc 3 màn hình của 3 acc: main acc + sub acc 1 + sub acc 2 - Khi sub acc 1 chat thì + Main acc: hiển thị tin nhắn mới + Sub acc 2: không hiển thị (reload lại thì có) Mong muốn: - Đồng bộ tin nhẵn giữa các tài khoản giống nhau và hiện được tin nhắn mới | https://drive.google.com/file/d/13M34a0dJwLpr9qjP7Na8iuAZap_su3R8/view?usp=sharing | New | Normal

## Test data
TEST DATA USE FOR TEST CASE
ID & Sub ID | Test data name | Short description | Data | Note status | Count use
TD - 01 |  |  |  |  | 0
TD 01 - Sub ID 01 |  |  |  |  | 0
TD 01 - Sub ID 02 |  |  |  |  | 0
TD - 02 |  |  |  |  | 0
TD 02 - Sub ID 01 |  |  |  |  | 0
TD 02 - Sub ID 02 |  |  |  |  | 0

## Mindmap of TC
MINDMAP OF TEST CASE
No. | Mindmap name | Requirement | Mindmap of Group | Link mindmap | Reference
[5 empty] | Version | Type | Group feature | Feature | Sub-Feature
1
2
3
4
5
6
7
8
9
10

## Feature list
LIST FEATURE BY PLATFORM
Group feature | Feature | Sub feature | Sub - sub feature | Group ID of TCs | Document / Task
Group chat |  |  | Chat
| Check login |  | Login
|  | Not login | Not | Chat - Login - Not
|  | Logged in | Yes | Chat - Login - Yes
|  | Log out | Log out | Chat - Log out
| Message chat |  | Msg
|  | Header | Header | Chat - Msg - Header
|  | Footer | Footer | Chat - Msg - Footer
|  | Category | Category | Chat - Msg - Category
|  | Target | Target | Chat - Msg - Target
|  | Chat title | Title | Chat - Msg - Title
|  | Chat conversation | Conversation | Chat - Msg - Conversation
|  | Upload file | Upload file | Chat - Msg - Upload file
|  | Download file | Download | Chat - Msg - Download
|  | Delete file | Del File | Chat - Msg - Del File
|  | Chat footer | Footer | Chat - Msg - Footer
|  | Error | Error | Chat - Msg - Error
| Category logic |  | Category
|  | List item | List | Chat - Category - List
|  | Select item | Select | Chat - Category - Select
|  | Change another item | Change | Chat - Category - Change
| Target logic |  | Target
|  | Show list item follow selected category | List | Chat - Target - List
|  | Change another item | Change | Chat - Target - Change

## Bug report
Bugs Report
Bug group by status
| Group | Feature | Total bugs | Critical | [5 empty] | High | [5 empty] | Normal | [5 empty] | Low
|  | Name |  | New |  | Fixed |  | Done |  | New |  | Fixed |  | Done |  | New |  | Fixed |  | Done |  | New |  | Fixed |  | Done
|  |  |  | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | % | Total | %
Group 1
|  | Feature 1 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
|  | Feature 2 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Group 2
|  | Feature 3 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
|  | Feature 4 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!

## Bug Data Clickup
BUG LIST
Bug ID | Bug name | Status | Priority
27rqykv | [Gambaru website] Button add skill wrong effect when hover on if not select skill | Release Pro | Normal
2ate490 | [Event page] [Improve] Go to event when clicking on event card | Release Pro | Low
2akk79x | [Authen] UI - Need change format of text on page verify code | Release Pro | Low
2k68164 | [Profile client] Icon edit too small | Release Pro | Low
2hy8kw3 | [Authen] Popup change password successfully unlike design | Release Pro | Normal
2aec7ct | [Gambaru website] Hide some icon of page company detail | Release Pro | Normal
2k0eu7y | [Client sign up] Auto uncheck field term & privacy if click back to edit | Release Pro | Normal
2845zvm | [Gambaru website] Client - Text & format of button Save wrong some page | Release Pro | Normal
29qkkqd | [Export profile] Not show current salary at pdf after export | Release Pro | Normal
2gfug1m | [Export profile] Item "Education" can't get the date | Release Pro | Normal
29c2tye | [Gambaru website] Disable button delete if has a education infor | Release Pro | Low
2b4qwmz | [Staging][Event] Bugs UI Detail Event page | Release Pro | Normal
29qj0a6 | [Gambaru website] Remove call api top Job if login client account | Reject | Normal
2j9qxku | [Authen] Show wrong eye icon when show/hide password | Release Pro | Normal
2fzap65 | [Graph matching] Decrease line spacing of hint & change color of shadow | Release Pro | Normal
29qjwkw | [Export profile] Not show about me at pdf after export | Release Pro | Normal
2a8x0j2 | [Export profile] Text result of remotely show uppercase on pdf file | Release Pro | Low
2k69wd9 | [Client sign up] If not create password success then show message to user | Release Pro | Normal
29c2pk2 | [Gambaru website] Not change text to Saved after save job success | Reopen | Normal
2kbz3a9 | [Client sign up] Page preview if user not logo then show in correct | Release Pro | Normal
2a2dmu7 | [2FA][Bug UI] Enable 2FA page | Release Pro | Normal
2fky46w | [Graph matching] UI - Space between Nice to consider & no exp is short | Release Pro | Normal
2g537jd | [Authen] Change scroll bar of avatar list when sign up | Release Pro | Low
2adz459 | [2FA][Responsive] Bugs UI responsive | Release Pro | High
2b4pqh1 | [Authen] User can click check send verify code multi time if wrong code | Release Pro | Normal
2a8xwwk | [Export profile] Show empty avatar at pdf file if user not upload avatar | Release Pro | Normal
2cr6n9q | [Authen] Staging - Hide some menu of authen prepare deploy pro ver1.0 | Release Pro | High
2am40c9 | [Export profile] Not show year exp of soft skill at pdf file | Release Pro | Normal
2845tqn | [Gambaru website] Talent sign up - User cann't remove image after upload it | Pending | Normal
27jzpfm | [Client sign up] Authen - Button edit of page confirm email no effect when hover | Release Pro | Low
2am33mz | [Export profile] Not show salary & onboarding date at pdf file | Release Pro | High
2akjf3u | [Authen] UI - font weight of text page welcome unlike design | Release Pro | Low
2hrhm96 | [Event] Page provide information after submit email data not transkey | Release Pro | Normal
2k679u7 | [Gambaru website] Talent profile has a special character at level bar of language | Release Pro | Normal
2g52mhk | [Authen] Change default when user go direct link of authen | Release Pro | Normal
2atexv7 | [Profile] Not validate field First name, Last name when user edit | Release Pro | Normal
2d3v8td | [Authen] Cann't sign out after log in from gamba work | Release Pro | Normal
2jv0q7q | [Client sign up] Text Or of page select method no transkey | Release Pro | Normal
2atdnvu | [Profile] FB Auto switch to mode ON after connected with GG | Release Pro | High
2ccwk85 | [Authen] Phone flag icon & phone code is not center | Release Pro | Normal
2gfug03 | [Export profile] Incorrect date of birth | Release Pro | Normal
2b4w2rk | [Event] Show section event upcoming to Homepage talent | Release Pro | High
2adw2rk | [Wallet] Some point of popup show balance unlike design | Release Pro | Normal
2k685wj | [Profile client] Extend height of field about company | Release Pro | Low
2g530zy | [Authen] User can skip step confirm password when signup | Release Pro | Normal
2atdtp4 | [Event page] Bugs UI Event page | Release Pro | Normal
2j3vr96 | [Authen] UI of popup fill 2FA verify code not show desc below title | Release Pro | Normal
2amb5j3 | [Export profile] Not uncheck if move to next page at list talent pool | New | Normal
29qj5jn | [Gambaru website] Client cann't go to other page of website after finish step 1 of post job | Release Pro | Normal
2hrheh0 | [Event] Not censored email & phone | Release Pro | Normal
2k67bbf | [Client Signup] The expire page has not been translated into Japanese | Release Pro | Low
2g4f502 | [Export Profile] Export profile function not working | Release Pro | High
2atd7t6 | [2FA] Generate new QR code when rebuild 2FA | Release Pro | High
27k104k | [Talent sign up] Parse CV- If no choose other skill then cann't next other section | Release Pro | High
2k0ewmn | [Client sign up] Change color & under line text link of check box term, privacy | Release Pro | Normal
2a2e05b | [2FA] Cannot load page when clicking Disable 2FA | Release Pro | High
2k6a45c | [Gamba website] List year not auto add new year when go to next year | Release Pro | Normal
2a8x66m | [Export profile] Gender & birthday not show a row at pdf file | Release Pro | Low
2akmbzu | [Authen] Can use invalid email for sign up new account | Release Pro | Normal
2a8xm9w | [Export profile] Decrease space between element of language infor | Release Pro | Low
2aed6hx | [Export profile] Not show clearly other status of vetting at pdf file | Release Pro | Normal
2juqrv9 | [Client Signup] The information confirmation Page does not need to display the password field. | Release Pro | Low
2adx5ff | [Wallet] Remove line between other transaction & add space at left, right | Release Pro | Normal
2fkxnpc | [Graph matching] UI - Decrease font size some point | Release Pro | Normal
2ccwpng | [Authen] Show incorrect message when user fill wrong phone number | Release Pro | Normal
2akmvpy | [Authen] Press enter on verify code page but it not work | Release Pro | Normal
2a89958 | [Authen] User can click resend code multi time & wrong text | Release Pro | Normal
2fkx2t7 | [Graph matching] UI - Color of tech skill unlike design | Release Pro | Normal
2fk78jk | [Gambaru Website_Client] Remove "Phone" from Footer Page | Release Pro | Normal
2aecvq7 | [Export profile] Title & icon of tech skill, soft skill not show a row | Release Pro | Low
2aed0wa | [Export profile] Skill name show at pdf not beauty | Release Pro | Normal
2am36p7 | [Export profile] Not export profile if talent at offer & hire on vetting | Release Pro | High
2k0ev3y | [Client sign up] Hide fields pass & confirm if back from page preview | Release Pro | Normal
2b4qk1r | [Staging][Event] Bugs UI Event page | Release Pro | Normal
2k688qq | [Profile client] Delete logo icon position not incorrect | Release Pro | Normal
29huv28 | [Gambaru website] Talent cann't accept invite invitation from client | Release Pro | High
2a8x4ta | [Export profile] Wrong title about talent of section PI at pdf file | Release Pro | Low
2jn95j0 | [Client Sign Up] Style of Password is incorrect | Release Pro | Low
2atf86r | [Profile] Edit title & placeholder of some fields | Release Pro | Low
2fkygbz | [Home Play] Bugs UI Home Play | Release Pro | Normal
2k68v5t | [Client profile] Change style of text character left of field about company | Release Pro | Normal
28fn7an | [Gambaru website] Talent view private job then skill show override default logo | Release Pro | Normal
27rqacd | [Gambaru website] Change rule or remove button increase, decrease of salary | Release Pro | Low
2hrhgu6 | [Event] Page provide button continue different design | Release Pro | Normal
2am424v | [Export profile] Not show matching percent of soft skill at pdf file | Release Pro | Normal
290k7cu | [Authen] Show wrong icon of special characters when user choose ? character | Release Pro | Normal
2am3k80 | [Export profile] About of talent show pdf no understand enter character | Release Pro | Normal
2hrjf1k | [Event] Not go to fill infor page if user reload page | Release Pro | Low
29c2xhd | [Gambaru website] Can search university name & major name | Release Pro | Low
2kbye37 | [Gambaru website] Text of language level when post job format right | Release Pro | Normal
2jn3yj3 | [Gamba website] Change some point of email sent registration link to client | Release Pro | Low
2k6a3eb | [WORK] Build Profile: Error "Duplicate data" after user completes profile but can't go further | Release Pro | Critical
2845wnp | [Gambaru website] Talent sign up - Change logic when update infor of page preview at some sections | Release Pro | Normal
2k0exbd | [Client sign up] Cann't finish client sign up | Release Pro | High
2aen0xp | [Export profile] Show html code of interview message at pdf file | Release Pro | Normal
2a8x2re | [Gambaru website] Not show level bar of language at talent detail page | Release Pro | Normal
2ate3kf | [Profile] Change border color of button after user click | Release Pro | Normal
27k0xge | [Talent sign up] Parse CV - Email of field email change to email of CV | Release Pro | Normal
2aed821 | [Export profile] Add section language at pdf file of vetting talent detail | Release Pro | Normal
2am43gx | [Export profile] Not show language level bar of pdf file | Release Pro | Normal
2am3r0m | [Export profile] Month of WE missing 1 month at pdf file | Release Pro | Normal
2ccxh0j | [Authen] Handle response error code from firebase | Release Pro | Low
2adwc69 | [Wallet] Remove border of button Connect wallet on balance popup | Release Pro | Normal
2hrhxgm | [Event] The content and other of topics in the "Favorited topics" section is not correct | Release Pro | Normal
2adxt5c | [Wallet] Has a spase on first & last option of field filter | Release Pro | Normal
2b4q5hc | [Authen] Cann't enter & not auto enter when user type GG Auth code | Release Pro | Normal
2b4qcy3 | [Profile] Not auto switch mode ON at social link if sign up connect with GG or FB | Release Pro | Normal
2a8xrnc | [Export profile] Avatar of talent after export is broke layout | Reject | Normal
2k68pu3 | [Client sign up] User can click button Preview when it disable | Release Pro | Low
2k6ape2 | [Client sign up] Contact email not auto fill | Release Pro | Normal
2kbxpc3 | [Gambaru website] Button "Let's start" of page profile approve not redirect after click | Release Pro | Normal
2845ehv | [Gambaru website] Talent sign up - Remove default value is 0 of salary fields | Release Pro | Normal
2aed443 | [Export profile] Not show reason & advice if it empty data at pdf file | Release Pro | Normal
2k67n3x | [Gambaru website] Text Log in when hover unlike button Sign up | Release Pro | Low
290k95p | [Gambaru website] Button add skill wrong effect when hover out after selected skill | Release Pro | Normal
2ategmy | [Profile] Not validate field Nickname when user edit | Release Pro | Normal
2d3vgqg | [Gamba website] Talent after sign up then don't have language infor | Release Pro | Normal
2jfbz00 | [Gambaru website] Education of sign up - Start date less than end date but show error message | Release Pro | Normal
2aemq6d | [Export profile] Not show character [] at year exp of skill | Release Pro | Normal
2cjj9eg | [Authen] Sign in - sent many request on server when user enter many time | Release Pro | Low
27rpa5n | [Gambaru website] Text area not consistency - need change 1 style | Pending | Normal
29hv24k | [View matching score] Remove matching score bar of list job on page company detail | Release Pro | Low
2advf0k | [IDO Landing page][Bugs UI] IDO Landing Page | Release Pro | Normal
2am44xv | [Gambaru website] Language level is none but show percent at profile detail page | New | Normal
2akm1n7 | [Authen] UI - Suggest Need effect when user click or press enter on the submit button | Release Pro | Low
290w5f6 | [Gambaru website] Change message if parcv not result | Release Pro | Low
27rnqp4 | [Authen] Show method connect wallet but cann't click & show text coming soon if hover on | Reopen | Normal
2adwz68 | [Wallet] Height of field filter less than search field | Release Pro | Normal
29qjkkh | [Export profile] Cann't export profile if has skill with special character of skill name | Release Pro | Normal
2cjkerp | [Authen] Not show error message when user fill wrong 2FA code when login | Release Pro | Normal
2k0ettt | [Client signup] Not limit max characters of password | Release Pro | Normal
2jn8aq4 | [Client Sign Up] No go to 'Thank for the registration' page and no send link to the mail, after click 'registration' button | Release Pro | Low
2aece3t | [Gambaru website] Not show language section of vetting talent detail page | Release Pro | Normal
2hy7nq8 | [Authen] Add link for term of use & Privacy | Release Pro | Normal
2jn9eyk | [Client Signup] Fill Information Page Not Japanese | Release Pro | Low
2jv0qnt | [Client sign up] Not show validate if email empty & user click next button | Release Pro | Normal
2b4pkk7 | [Authen] Not auto enter when user fill 6 characters of verify code | Release Pro | Low
2ccz4ur | [Authen] Not connect Google acc | Release Pro | High
2akkp54 | [Authen] UI - Need change some point on screen continue with social | Release Pro | Low
2am3mak | [Gambaru website] Highlight talent begin date incorrect | New | Normal
2ccxydv | [Authen] Not show message to user when fill wrong password | Release Pro | High
2ccybba | [Authen] Not show message wrong verify code if copy paste it | Release Pro | Normal
2g4f1gw | [Export profile] Add the number of checkbox selected in the export profile button | Release Pro | Low
2hrhyug | [Event] Error validation rules | Release Pro | Normal
2a8xcgb | [Export profile] Position not same column with level & year exp not format bold | Release Pro | Low
2845grr | [Gambaru website] Talent sign up - Not close popup fill WE if click out popup | Release Pro | Normal
2kbyngj | [Client sign up] Sign up with GG not show register email & cann't change it | Release Pro | High
2am3zpd | [Export profile] Not uppercase name of year exp skill | Release Pro | Low
2akhd4h | [2FA] Show border Cancel button in Disable popup | Release Pro | Normal
290vywh | [Gambaru website] Not show avatar & infor of talent at chat box header in the first time | Release Pro | Normal
2adwgh0 | [Wallet] Color of text on page transaction history unlike design | Release Pro | Normal
290nr9g | [Authen] Draw auth flowchart | Release Pro | Low
2k0etcm | [Client sign up] Show incorrect eye icon of password field | Release Pro | Normal
2fkymty | [Home Gamba Play] Bugs UI Home Gamba Play | Release Pro | Normal
2az7vaq | [Authen] Cann't use authen on Firefox | Release Pro | High
29qhxny | [Graph matching] Not show matching result on staging | Release Pro | High
2atduza | [Profile] Remove step click button Edit user can update profile | Release Pro | High
2g53e1a | [Authen] Add border & background color for avatar when sign up | Release Pro | Normal
2aed2aw | [Export profile] Salary at pdf not format currency | Release Pro | Low
2hrh4q8 | [Event] Page provide email not transkey some point | Release Pro | Normal
2advztr | [IDO Landing page][Responsive] NOT reset status button when clicking on button on IDO Landing Page | Release Pro | Normal
2gfug9m | [Export profile] Work Experience infor not correct when show pdf file | Release Pro | High
2kc11fb | [WORK] Build Profile: Taking countless time to parse CV from pdf but no completion | Release Pro | Critical
2ccyyq1 | [Authen] Migrate data need process acc sign up with GG acc | Release Pro | Normal
27rnx02 | [Gamba website] Client - contact page - Change style of field message same other text area | Release Pro | Low
2a8xy9f | [Gambaru website] Defaut avatar of user show incorrect if user not upload avatar | Release Pro | Normal
2k6852p | [WORK] Build Profile: Bot always ask user's email although user has provided already | Release Pro | High
283zpe4 | [Gambaru website] Change message error if duplicate phone | Release Pro | Normal
28fmvuf | [Gambaru website] If user change link or close tab create job then auto save data of job | Release Pro | Normal
2j9p67w | [Authen] Find reason of show message recapcha & not continue when login phone multi time | New | Low
2cczkbn | [Authen] Show message acc disable when fill password wrong many time | Release Pro | Normal
2kc1gpf | [Client sign up] Client cann't continue if not finish sign up and back to homepage | Release Pro | Normal
2fkxw1d | [Graph matching] UI - Text color of exact matching incorrect | Release Pro | Normal
27rp9eq | [Gambaru website] Some page suggest change default scrollbar become custom scrollbar | Pending | Low
2adz3zp | [Wallet] Not responsive on mobile | Release Pro | High
27rp9vk | [Gambaru website] Some page suggest change default list become custom list | Pending | Normal
2adxeey | [Wallet] Change color of boder when user click on search, filter fields | Release Pro | Normal
29qhw2m | [Gambaru website] Api Candidate vetting response Internal server error | Release Pro | High
2aedcrg | [Export profile] Re-format type of section major | Release Pro | Normal
2hy6djj | [Authen] Not show radius when hover button method | Release Pro | Normal
2akk0q7 | [Authen] UI - Suggest need change border of textbox after click | Release Pro | Low
2a8xqdb | [Export profile] Remove level of education at pdf file | Release Pro | Normal
2a892yg | [Authen] Not paste verify code copied from email to auth page | Release Pro | Normal
290kcxk | [Gambaru website] Duplicate data of WE when user add new | Release Pro | Normal
28fm0av | [Demo request] Need infor of CV & JD user demo to investor | Release Pro | Normal
2845aef | [Gambaru website] Talent sign up - User can expand section PI & edit after next | Reject | Normal
2aeda0a | [Export profile] Not show email & phone at pdf talent vetting detail | Release Pro | Normal
2jfbz8q | [Gambaru website] Talent sign up 'Language' section: UI is broken | Release Pro | Normal
2jn904f | [Client Sign Up] Edit UI of the Signup Page (Content&UI) | Release Pro | Low
2k6apx1 | [Client sign up] Change position of text image can upload & add icon delete | Release Pro | Normal
2atezhf | [Profile] Add option not gender on list gender option | Release Pro | Low
2hrhaha | [Event] Required input email event signed in | Release Pro | Low
2adyqyb | [Wallet] Change height of button withdraw & more radius of wallet connected | Release Pro | Normal
290n0n6 | [Gambaru website] Add link of job at page candidate detail | Release Pro | Low
2am4h8m | [Export profile] Not show status payment fail or success at pdf file | Release Pro | Normal
2k686a2 | [Authen] Password validation shows inappropriate message | Release Pro | High
2hrj9nb | [Event] If user use email too long then truncate when show it | Release Pro | Low
2jur14z | [Gamba website] Change matching job at footer to search job | Release Pro | Normal
2atdabt | [Profile] Incorrect link url of profile page if click on avatar | Release Pro | Normal
2aemtch | [Export profile] Show wrong format date & time interview at pdf file | Release Pro | Normal
29hupkf | [Gambaru website] Private job but show all infor of talent on Job saved tab | Release Pro | Normal
28fmrrd | [Gambaru website] Broke layout of currency when client set salary for talent | Release Pro | Normal
29c2m5q | [View matching score] Not has transkey of text View matching score | Release Pro | Normal
2akjk0h | [Authen] UI - Some points of screen connect Email unlike design | Release Pro | Low
2k0er38 | [Client sign up] Decrease space between some fields | Release Pro | Low
2a88wv0 | [Authen] Text of button "Continue with Email/Phone" not consistency | Release Pro | Low
2cjkwem | [Authen] Change flow show page verify code on some case | Release Pro | Low
2b4qzze | [Authen] Use phone number sign up then cann't next at step check verify code | Release Pro | High
2fzag1y | [Graph matching] UI - Not show section Language in page on-process vetting | Release Pro | Normal
27ygmj5 | [Gambaru website] Issue of production | Fixing | Low
2hrhpn9 | [Event] Require input Optional fields | Release Pro | Low
2d3v4f2 | [Authen] Talent acc was updated review status but after log in redirect wrong link | Release Pro | Normal
28fmytf | [Gambaru website] Not expand popup if client click icon choose onboard date in candidate | Release Pro | Normal
2ccwev0 | [Authen] Sign in - Not auto focus to password field after fill email | Release Pro | Normal
2am3xqn | [Export profile] Pdf file not show infor of i icon at matching infor if has skill data | Release Pro | Normal
2cjjmzr | [Authen] Sign in - Not show message to user if fill wrong verify code | Release Pro | Normal
2k68kej | [Client sign up] Page thanks you responsive not good on mobile | Release Pro | Low
28fkyek | [Gambaru website] All job list page - Filter of salary range show not enough | Release Pro | Normal
2atf46p | [Event page] Not return to the same scroll position when using browser's back button | Release Pro | Normal
2jv0prz | [Event] Gambaru user registered but show button register now | Release Pro | Normal
29hun2n | [View matching score] Show matching score at invited job detail page | Release Pro | High
29ht3b7 | [Hot fix] Show text maintenance when talent hover on option build profile with AI Chatbot | Release Pro | Critical
2atf1n0 | [Profile] Wait response from server when user submit update profile | Release Pro | Normal
2akk22a | [Authen] UI - Decrease font size of text on page forgot password | Release Pro | Low
29qkakk | [Export profile] Not show country at pdf after export | Release Pro | Normal
2aecurh | [Export profile] Change position of icon i at matching score result | Release Pro | Low
28fkx4t | [Gambaru website] Update term & privacy of JP language | Release Pro | High
2a2dqc1 | [2FA][Bug UI] Disable 2FA page | Release Pro | Normal
2cjk4va | [Profile] Show wrong text when disconnect with Social acc was connected | Release Pro | High
2ategut | [Event page][Detail event page] Bugs UI Detail event page | Release Pro | Normal
2b4pdug | [Authen] Not show email, phone of user on verify code page | Release Pro | Normal
2jn96e3 | [Client SignUp] "Thank you for your Registration" page Not Japanese | Release Pro | Low
27rpd8e | [Gambaru website] Company detail page - break 2 api get infor | Release Pro | Normal
2ggh3ja | [Minigame] User can't click arrow left, right icon on instruction popup | Release Pro | Normal
29qj7cd | [Gambaru website] Not show JD & JR after back to page post job | Release Pro | Normal
2atdqfk | [Profile] Not show message to user if GG acc was connected with other acc | Release Pro | Normal
2b4px0m | [Authen] QR code on popup Verify GG Auth not center | Release Pro | Normal
2fkyj38 | [Graph matching] UI - Not change text to view less after click view more | Release Pro | Normal
2j3vcun | [Authen] Authen not recieve language type when redirect from gambawork | Release Pro | Normal
27k03fq | [Gambaru website] Special acc client wrong config of server chat | Release Pro | Normal

## Data
DATA USE FOR TEST CASE & BUG
Test Type |  |  | Test execute status |  |  | Bug status | Priority | Tested by | Test execute status
Quality Dimension | Test type | Full name for test type | Result | Full name of result | Meaningful | Status | Priority | Tested by | Status | Meaning
Functionality | FUN | Function test | T | Tested | Test case has run | Release Pro | Low | Khánh Nguyễn | Pass | Actual result matches its expected result.
| SEC | Security test | NT | Not test | Don't execute because of some reasons although they are planned to test. | Reject | Normal | Tâm Phạm | Fail | Actual result does not match its expected result
| VOL | Volume test | N/A | Not available | Some cases are composed at the beginning, however they are not useful in test execution phase because of Change requests… | Reopen | High |  | Blocked | Cannot be executed
Usability | USE | Usability test |  |  |  | Pending | Critical |  | Not Run | not executed during test iteration
Reliability | ITR | Integrity test |  |  |  | New
| STR | Structure test |  |  |  | Fixed
| STS | Stress test
Performance | BEN | Benchmark test
| CNT | Contention test
| LOA | Load test
| PER | Performance profile
Supportability | CON | Configuration test
| INS | Installation test